# 2.6.- ASSESSMENT OF PROGRESS, RECOMMENDATIONS AND COCLUSIONS IN THE REPORTING PERIOD

During the reported period, Twinning Project team was able to produce the materials on the time scheduled and with a deep, comprehensive and quality work.

Components 1, 2 (General principles and Mechanisms for the Realization of the Magistrates’ Disciplinary Liability) and 4 (Criteria and Mechanisms for the verification of the work performed by the Magistrates) were finished in the previous quarter.

In the reporting period two National Seminars regarding these two components were successfully held.

Component 3 (criteria and mechanisms for the selection, appointment, promotion and downgrading of magistrates) and 6 (strengthening the capacity of the SJC) finished and the final experts’ recommendations were presented by the RTA to the SJC on the 5 and 21 June 2006..

As a result of the activities implemented so far on the basis of the framework document (activity 1.2) and the conclusions of the seminar (activity 1.3) - both approved by the SJC on 30 November 2005-  we produced recommendations and proposals in the areas covered by this project related to:

- The Constitutional reform

- The amendments to the Judicial System Act

- Legislation concerning the Independence of Judges, Prosecutors and Investigators

- Legislation concerning the Rights and Obligations of Judges, Prosecutors and investigators

- Legislation concerning the Disciplinary Liability of Judges, Prosecutors and Investigators

- Legislation related to the criteria and mechanisms for the selection, appointment, promotion and downgrading of magistrates

- Legislation concerning the Magistrates’ Administrative Situation.

- Legislation concerning evaluation

- Amend the existing Regulation concerning the Operation of the SJC and its Administration in view of setting up a new Evaluation and Supervision Department

- Proposal to the Ministry of Justice for a minor reform in the JSA allowing judges, prosecutors and investigators to be appointed in the said new Evaluation and Supervision Department and introducing the right of evaluated magistrates to appeal against SJC decisions concerning evaluation. It was suggested to the SJC to communicate this recommendation to the Ministry of Justice.

- Provisions ensuring funding for the new Evaluation and Supervision Department of the SJC.

- Amendment to section 5 of chapter 6 from article 77 of the Regulation concerning the Operation of the SJC and its Administration.

In the previous quarterly report it was referred:

The acceptance of these recommendations regarding the Constitution (new item 16 in article 84, new paragraph 4 in article 129 and new article 130a) was non existent (see in annex point 2.9.8) and regarding the amendment in the Judicial System Act was imperceptible although in the report produced on 28 November 2005 the conclusion was that “although the proposals for reform presented by the Ministry of Justice introduced positive improvements in the selection of junior magistrates and in the new draft of articles 147 (2) and 148 (3), its scope is clearly too short and does not give all the necessary and expected answers to satisfy the current necessities and concerns about the situation of the justice system in Bulgaria” (see in annex details in 2.9.9).

The assessment is that the reforms in the main legislation, as was mentioned in the report by Mrs. Schuster after the 4 peer review, is that  “…The expert finds some of these amendments very worrisome. These concerns stem from the content as well as the way the amendments were drafted and brought into Parliament…” …. “To the expert the way these crucial and extremely sensitive amendments were drafted is a clear sign of the lack of structure and vision in implementing a legal reform strategy and additionally the complete lack of understanding of the meaning of basic principles shared by the EU member states e.g. the rule of law and the independence of the judiciary.”

Mr. Kjell Björnberg in his report for the 4th peer review points out that  “…parts of the proposed amendments to the Bulgarian Constitution, to which I will come back below, not only fails to enshrine the independence of the judiciary in the Constitution, but must furthermore be seen as a step backwards in the process of creating an independent judiciary and can be seen as serving to undermine the independence of judges by creating a closer connection of their administrative functions to the executive branch of the government”.

Although it has been said that this reform in the main legislation introduces no fundamental changes, it really establishes critical and very substantial reforms.

The reform in the primary legislation is for the most part against and in the opposite direction to the recommendations made by this Twinning Project. These recommendations are based on some key and very fundamental principles:

- Clear division of powers (Minister-Ministry of Justice #  Supreme Judicial Council)

- Principle of independence of the SJC (including budgetary independence)

- Strengthening the SJC

- Principle of independence of Judges, Prosecutors and Investigators (independency ad extra and ad intra –limitation of the role of Administrative Heads-)

- Full accountability of magistrates as a correlative consequence of their independency

- Improvement of magistrates’ legal status

All the recommendations and proposals produced intended to fill with real content the mentioned principles.

As for the secondary legislation, the proposals for Ordinances to the Supreme Judicial Council and related recommendations the situation is as follows:

- Ordinance concerning the Independence of Judges, Prosecutors and investigators: on 5 April 2006 the SJC only acquainted the proposals.

- Ordinance concerning the Rights and Obligations of Judges, Prosecutors and investigators: on 5 April 2006 the SJC only acquainted the proposals.

- Ordinance concerning the Disciplinary Liability of Judges, Prosecutors and Investigators: on 5 April 2006 the SJC only acquainted the proposals.

- Ordinance concerning the Magistrates’ Administrative Situation: on 5 April 2006 the SJC only acquainted the proposals.

- Ordinance on evaluation: on 29 March 2006 the SJC decided to prolong the term for its approval for one month.

From the Twinning Project it was highlighted the need to eliminate the Inspectorate Service in the Ministry of Justice, to establish an Evaluation and Supervision Department in the SJC and to avoid evaluation on a regional or local basis through the Administrative Heads or regional panels.

- Reform the current Regulation about the Work and Activity of the SJC and its Administration in order to create in the SJC a new Evaluation and Supervision Department: as above.

- Previsions to provide the new Evaluation and Supervision Department of the SJC with the consequent budgetary coverage: as above.

- Proposal to the Ministry of Justice for a minor reform in the JSA in order to allow judges, prosecutors and investigators to be appointed for this new Evaluation and Supervision Department and to establish the right of evaluated magistrates to appeal against the SJC decisions concerning the evaluation. It was suggested to the SJC to communicate this recommendation to the Ministry of Justice: no news from this.

- Amendment in the “Regulation for the work of the SJC and its Administration” in section 5 of chapter 6 from article 77s.

Nevertheless, the drafting of a secondary legislation cannot be properly done if its pillars, that is, the main legislation (Constitution and Judicial System Act), does not recognise the proper principles, structure and requirements.” …  …  …

In the previous quarterly report (3 May 2006) a summary list of some recommendations not reflected in the amendments of the legislation on the justice system in Bulgaria was also included. It is necessary again to mention here these identified needs:

- There is not a description of the content or a definition the independence principle in the Bulgarian law.

- There is not a definition of the Supreme Judicial Council in the Bulgarian Constitution as the independent institution in charge of managing and governing the judiciary.

- Improvement of the principles of independency and accountability of magistrates in article 132 of the Constitution (magistrates need full independency and full accountability in the performance of their public duties not immunity, only mechanisms to protect their independency from arbitrary attacks)

- The full governance of the judiciary should remain in the SJC, with no intervention of the executive (independency ad extra) nor competence or outstanding role of the administrative heads (independency ad intra) on the professional status of magistrates.

- The Minister of Justice, as well as any representative of the Ministry of Justice, should be fully removed from the SJC.

- The SJC should be chaired by a chairperson, who will represent the SJC and chair the institution. Now this is a collective institution representing judges, prosecutors and investigators with no chairperson. Recommendations to fill this gap in order to:

  - Have its representation role before the citizens and the rest of the public powers

  - Talk for and defend the interests of this institution

  - Avoid conflict of interests

  - Be accountable for the judicial power

  - Strengthen the institution

- The SJC working system and conceptual definition: the SJC should either be a permanent institution or have a Permanent Commission.

- The SJC anti-corruption commission should recover its investigation powers

- The responsibility for submitting annual reports on the activities of the judiciary to the Parliament should remain under competence of the SJC through its chairperson (now inexistent) and not in the way fixed in the new item 16 in article 84 of the Constitution.

- The dismissal of the chairpersons of the Supreme Court of Cassation, the Supreme Administrative Court and the Prosecutor General before the National Assembly as it is now approved in article 129 of the Constitution is clearly inadequate:

  - Weakens the SJC taking out this competence

  - Political criteria and control in the dismissal of the main position of the judiciary precisely on the grounds that will require evaluation of their work and of their behaviour

  - Reduction of guarantees in the dismissal of these main positions

  - Breach of the principle of independency in the aspect related to the need of the intervention of an authority independent of the executive and legislative power in every issue related to the termination of office of these main positions

  - If the current regulation is considered inadequate, an eventual reform should seek to reinforce the principles of independency, separation of power and the role of the SJC as the governing institution of the judiciary, providing it with a proper legal framework to develop its powers.

- New article 130 a) of the Constitution giving new powers of the Ministry of Justice is in the opposite direction to the commitments fixed in the the UE Council Decision of 19 May 2003 on the principles, priorities, intermediate objectives and conditions  in the Accession Partnership with Bulgaria and against the recommendations made:

  - Takes out to the Minister competences of the SJC, weakening the institution: it is opposite to the reinforcement of the SJC

  - Damages to the principle of separation of power and the need to clearly distinguish between the roles of the SJC and of the Ministry of Justice

  - Affect the principle of economic independency

  - Not respect the principle of independency in the aspect related to the need of the intervention of an authority independent of the executive and legislative power in every issue related to the selection, recruitment, appointment, career progress or termination of office of magistrates

  - Affect the current autonomy of the National Institute of Justice from the executive or legislative

  - “Control” by the Minister of the work the magistrates: contravene the principle of independency: independency cannot be controlled but submitted to a sounded liability.

- The SJC should obtain its own administration and finances, draft and propose the budget for the judiciary through  the chairperson now inexistent in the JC (not the Minister of Justice)

It should be necessary to eliminate the inspectorate service from the Ministry of Justice and to create an Evaluation and Supervision Department  inside the SJC. For this there is the need of a minor reform in the JSA in order to allow judges, prosecutors and investigators to be appointed for this new Evaluation and Supervision Department (the same as they can be

- Competence for selection, appointment, promotion or downgrading should be exclusively given to the SJC. The role of the administrative heads should be limited only to the designation of the number of vacancies in their respective courts or offices.

- The SJC should be entitled to develop regulations on the magistrates’ legal status. In this sense article amendment in article 27 (11) of the JSA was proposed giving the SJC with competence “To adopt regulations implementing this law related to the magistrates´ legal status as governing institution of judges, prosecutors and investigators, and to adopt regulations related to the work of the SJC and its administration.”

- As for District Magistrates: Change in all art 127 JSA the word “person” by the words “judges, prosecutors or investigators”, to avoid appointment of persons who previously are not judges, prosecutors or investigators. No other way in but competition.

- Limit the role of the administrative heads to the proposals to the SJC only for determining the number of magistrates requires, eliminating in article 30.1 JSA eliminate the words “appointment, promotion, moving and discharge”. This shall be decided independently by the SJC

- Regarding the appointment of Administrative Heads, change in all art 125 b) JSA the word “person” by the words “judges, prosecutors or investigators”, to avoid appointment in the main positions or administrative heads of persons who previously are not previously judges, prosecutors or investigators. Demoralization of magistrates

- As for the promotion, nowadays the promotion and moving of judges, prosecutors and investigators is mainly conducted from a local point of view. It is necessary to change to a national perspective in which all judges, prosecutors and investigators were able to apply directly and only to the SJC for any position wherever it is, either to a superior position or to an equal level one, by a public merit concurs under the principles of equality, merit and capacity publicly announced and decided by the SJC without interference of administrative heads.

- For this, there is a need to reinforce the departments and the administration in the SJC, creating a new Evaluation and Supervision Department in the SJC to make a real evaluation of candidates for promotion of magistrates, providing the Commission for Proposals with the objective data and with the information necessary for it to take a the decision about who should be promoted.  This evaluation should not be made at local or regional level by the Administrative Heads or auxiliary local panels.

- As for the Disciplinary liability of magistrates, need for legal habilitation to the SJC in the SJA for approval of an ordinance or regulation on this issue. No intervention of Minister of Justice and no role of Administrative Heads except for minor offences. Procedural guarantee, fundamental principles established and need to graduate the infringement by amending art 168 of the JSA (as follows “For guilty neglecting of their official duties, as well as for violation of the rules of the professional ethics, the judges, prosecutors and investigators shall bear disciplinary responsibility, in accordance with the severity of the violation and the classification thereof as very serious infractions, major and minor infractions under the Regulation for magistrates liability approved by the Supreme Judicial Council")

- As for the secondary legislation, recommendations have been made for

  - Ordinance concerning the Independence of Judges, Prosecutors and investigators

      - SECTION I. INDEPENDENCE INSIDE THE JUDICIAL SYSTEM

        - A) Judges

        - B) Prosecutors and Investigators.

      - SECTION II. INDEPENDENCE IN RELATION TO OTHERS BRANCHES OF GOVERNMENT

      - SECTION III. LEGAL REMEDIES (GUARANTEES AGAINST ILLEGAL INFLUENCE)

      - SECTION IV. IMPARTIALITY PRINCIPLE (DEFINITION)

      - SECTION V. LEGAL EFECTS

      - SECTION VI  RECUSAL

      - SECTION VII REQUEST FOR THE DISQUALIFICATION OF A JUDGE OR PROSECUTOR

      - SECTION IV PROCEDURE

  - Ordinance concerning the Rights and Obligations of Judges, Prosecutors and investigators

      - CHAPTER I  PROFESSIONAL RIGHTS

      - CHAPTER II   PROFESSIONAL DUTIES

        - SECTION I	GENERAL PROVISIONS

        - SECTION II	JUDGES

        - SECTION III	PROSECUTORS

        - SECTION IV	INVESTIGATORS

        - SECTION V	. RELATIONS OF JUDGES, PROSECUTORS AND INVESTIGATORS

      - CHAPTER II	OFFICE LIMITATIONS. ACTIVITIES INCOMPATIBLE TO THE OFFICE HELD.

      - CHAPTER III	TENURE AND IMMUNITY. LEGAL EFFECTS

  - Ordinance concerning the Disciplinary Liability of Judges, Prosecutors and Investigators

      - CHAPTER I. GENERAL PRINCIPLES

      - CHAPTER II. Persons Subject to Disciplinary Liability

      - CHAPTER III. Breaches of Discipline

        - Section I. Judges

        - Section II. Prosecutors

        - Section III.- Investigators

      - CHAPTER IV. Disciplinary Sanctions

      - CHAPTER V. Extinguishment of Disciplinary Liability

      - CHAPTER  VI. Disciplinary Proceedings

        - (a) Competent Authorities

        - (b) Commencement and Progress of Proceedings

        - (c) Completion of Proceedings

        - (d) Appeal

  - Ordinance concerning the Magistrates’ Administrative Situation.

CHAPTER I: Administrative status, holidays and time-off

        - Section I	ADMINISTRATIVE STATUS

        - Section II HOLIDAYS

        - Section III   TIME OFF

  - Ordinance on evaluation

      - Section I General Provisions

      - Section II Grounds for Appraisal

      - Section III Subject-Matter and Criteria for Appraisal of Judges, Prosecutors and Investigators

      - Section IV Indicators for Appraisal of Judges

      - Section V Indicators for Appraisal of Prosecutors

      - Section VI Indicators for Appraisal of Investigators

      - Section VII Methods of Appraisal.

      - Section VIII Unified Form

      - Section IX Competent Bodies and Appraisal Procedures

      - CONCLUDING PROVISIONS

      - Appendix UNIFIED FORM FOR APPRAISAL OF JUDGES, PROSECUTORS AND INVESTIGATORS

  - As for criteria and mechanisms for the selection, appointment, promotion and downgrading of magistrates the initial proposals were produced for draft articles and were officially presented on 13 April 2006.

TITLE 1 - GENERAL PROVISION, SELECTION, RECRUITMENT AND APOINTMENT OF MAGISTRATES

CHAPTER I - General provisions

CHAPTER II – Announcement of Competition

SECTION I - General Provisions on anticipated vacancies

SECTION II - Competition for Junior Judges, Junior Prosecutors and Junior Investigators

CHAPTER III - Application and eligibility rules for competition

SECTION I - Competition  (Convening announcement, requirements of applicants, exam papers, Examination Committee, Exam proceedings, competition of applicants)

SECTION II - Training period at the National Institute of Justice (term, legal status of candidates, final evaluation)

SECTION III - Appointment of junior judges, prosecutors and investigators and their legal status

CHAPTER IV - Direct appointment of judges, prosecutors and investigators  (Admission to the judicial bodies through a direct appointment process)

SECTION I- General principles, proposal and requirement of the applicants

SECTION II - Evaluation Committee

SECTION III - Evaluation principles and criteria. Decision making process

SECTION IV - Appointment

CHAPTER VI - Special provisions for Investigators

TITLE II - PROMOTION OF MAGISTRATES

CHAPTER I - General principles and criteria for the appointment to office

CHAPTER II - Organization of this Body

CHAPTER III - Procedure

CHAPTER IV - Appeal or judicial review

CHAPTER V - Specialization of Magistrates

CHAPTER VI - Special rules for the reappointment to different judicial bodies

TITLE III - DEMOTION OF JUDGES, PROSECUTORS AND INVESTIGATORS

CHAPTER I - General Provisions

CHAPTER II - Retirement

CHAPTER III - Incapacity

CHAPTER IV - Resignation

CHAPTER V – Discharge Following Disciplinary “Dismissal”

CHAPTER VI - Criminal liability

CHAPTER VII - Refusal of acquisition of irremovability status

CHAPTER VIII - Incompatibility

SECTION I - General Provisions

SECTION II - Compatibility statement procedure

SECTION III - Incompatibility as a cause of discharge

CHAPTER IX - Return after temporary substitutions

CHAPTER X - Reinstatement to office of an unlawfully dismissed judge, prosecutor or investigator

CHAPTER XI - Reinstatement

  - Reform the current Regulation about the Work and Activity of the SJC and its Administration in order to create in the SJC a new Evaluation and Supervision Department

  - Proposal to the Ministry of Justice for a minor reform in the JSA in order to allow judges, prosecutors and investigators to be appointed for this new Evaluation and Supervision Department and to establish the right of evaluated magistrates to appeal against the SJC decisions concerning the evaluation.

  - Previsions to provide the new Evaluation and Supervision Department of the SJC with the consequent budgetary coverage.

  - Amendment in the “Regulation for the work of the SJC and its Administration” in section 5 of chapter 6 from article 77.

- The legal position of the National Institute of Justice as a fully independent organ and its relation on one hand as free standing from the Ministry of Justice and on the other hand its connection to the Supreme Judicial Council should be clarified. The proposed amendment to the Constitution giving the Minister of Justice the competence to organize the magistrates’ qualification to be forsaken.

- Judges should be enabled to organise and form professional associations.

- The excessive number of courts should be reduced and the workload, premises, equipment etc. better counterbalanced between the courts.

- The possibility of introducing restrictions in bringing in new facts and evidence in proceedings after an appeal should be considered.

- The creation of a complete and functioning land-register built on a cadastral system should be given a high priority.

- Court presidents should be obliged to act in cases of misconduct by judges in the court.

However, a very positive step was made in June 2006 when the Action Plan was approved and some of the recommendations made by this Twinning Project were finally taken on board:

1)  Preparing constitutional amendments to eliminate ambiguities as regards the full respect of the independence of the Judiciary.

2)  Drawing up a new Judicial System Act (JSA)  in close cooperation with the NA and the experts from the Twinning project with Spain, including regular consultations with the EC concerning the Draft JSA.

3) The Draft JSA should:

- Include criteria for evaluation of the quality of magistrates’ work, and eventually provide for establishment of new commissions within the Supreme Judicial Council (SJC) to this end.

- Reconsider the generalised competition principle limiting it to the entry into the system.

- Regarding promotion etc. a real merit based career path should be developed, hence the importance of objective and uniform assessment (attestation) criteria and a unit in SJC to oversee implementation.

- Provide for establishment of a new Evaluation and Supervision Department.

- Limit the role of Administrative Heads: Competence for evaluation, selection, appointment, promotion or downgrading should be exclusively given to the SJC.

- The role of administrative heads should be limited only to designating the number of vacancies in their respective courts or offices with no outstanding role in magistrates’ career development.

- Consult with Spanish Twinning in SJC.

The real transposition in the main legislation of these principles identified in the Action Plan must be taken place.

However, up to now this project has not received any communication whatsoever regarding the Action Plan implementation and, therefore, to our regret, we cannot avoid reporting the lack of any co-operation whatsoever between this project in the SJC and the MoJ, not even mere communication. This situation makes it impossible for this Twinning Project to assess the extent to which the Action Plan has been implemented in its aspects related to this Project.

Concerning the development of secondary legislation, having analysed the Action Plan, the experts in the last component 3 activity arrived at the conclusion that “These measures and principles are not yet reflected in the main legislation, and so it is highly recommended to wait for this implementation in the main legislation before developing the JSC secondary legislation, better than going in a direction that will go against the approved “Action Plan”….

In this sense, the RTA had several meetings in the SJC and finally filed a proposal in writing with the Legal Policy Commission and members of the SJC (letter dated 21st June 2006) as follows: before the SJC finalises new ordinances, it had better wait for the transposition of the Action Plan in the primary legislation, in order to take into account and be in accordance with the measures implementing the European Commission recommendations made in its Comprehensive Monitoring Report of 16 May 2006

However the SJC on 15 June 2006 approved the Ordinance for appraisal of Magistrates and on 28 June 2006 approved the Ordinance for rules and provisions for competitions for magistrates (final version). Consequently, main principles that inspired this project recommendations and the principles reflected in the Action Plan could not be included in these new ordinances.

# Footnotes

Detailed information of the activities, the results, all the recommendations produced by  this Twinning Project and the regular assessments can be found at:

http://www.vss.justice.bg/bg/enter.html

As it was previously precised, this Twinning Project never recommended the elaboration of a full new Law on Judiciary.

Anyway, the utmost importance of this kind of legislative initiative should never be developed in a hurry or under any kind of preasure circumstances.